## Sheet1
WBS Number | Task Name | WBS Description | Must Start by Date | Must End by Date | Task Level of Effort (in hours) | Task Duration (in days) | Predecessor (Finish-to-Start Dependency) (comma separated) | Resource Name(s) | Author (of Item for follow-on questions)
1 | BOOK MANAGEMENT | Managing the books or stock is the main component for LMS. We will need database to manage the books. | 2021-09-25 | 2021-09-28 | 10 | 3 |  | HTML,CSS,Python/SQL/JS | Uditi
1.1 | BOOK DETAILS | All necessary data about each book will be recorded
1.1.1 | Info about the book | Name, Author,Year of Publish & Review will be stored for referrence.
1.1.2 | Stock Details(ACCESSED BY ADMIN) | Details of how many copies are in library and with members.
1.1.3 | Borrower Details(ACCESSED BY ADMIN) | Details of the borrower of each copy of a given book.
1.2 | UPDATE | To add,remove and update details of books in the database.
2 | MEMBER DATABASE | The second main compoment in LMS is management of member records. | 2021-10-01 | 2021-10-06 | 12 | 4 | 1 | SQL | Khushi
2.1 | Member Information | Information of each member will be stored in the database
2.1.1 | Contact Details | Phone number, e-mail ID, address will be stored, along with name age and etc will be stored.
2.1.2 | Books borrowed | Details of each book borrowed will be stored.
2.1.3 | Payments made | Details of due payments, and whether the payment was before or after due date.
2.2 | Update Database | To add, remove or update the details of any given member.
3 | Fine generation | Fine management is an important concept in LMS in case the user doesn’t return the book on time | 2021-10-07 | 2021-10-11 | 6 | 3 | 1,2 | SQL,Python/JS | Nithish
3.1 | fine per day | fine per day is mentioned
3.2 | late by how many days | the difference between the actual return date and expected return date
3.3 | total fine | total fine should be displayed in the payment section for the user.
4 | LOGIN/SIGN-UP PAGE | Users can uses this page to create or login to their account. | 2021-10-13 | 2021-10-20 | 12 | 5 |  | HTML,CSS | Uditi
4.1 | LOGIN PAGE | Users with account can login to their account using their USER ID & PASSWORD.
4.2 | Sign up page | Users without account can use the Sign-Up option to create an account.
4.2.1 | ADMIN Sign-up page | Users can use this page to create an Admin account, if they have permission
4.2.2 | MEMBER Sign-up page | Users can use this page to create a Member account.
5 | HOME PAGE | This page is visible after logging in to the account | 2021-11-06 | 2021-11-12 | 10 | 5 | 1,4 | HTML,CSS,Python,AI,ML | Khushi
5.1 | Search bar | To search the books available in the library.
5.2 | Profile | Users can access their profile from the icon on the top right.
5.3 | Chat bot | Chat bot's basic function is for the user to help guide our website easily.
5.4 | Calendar | Shows the list of books that needs to be returned on a given date.
5.5 | BOOK CARD | Members can borrow books through this feature, which is available when member searches for a book and the display card of the book
5.5.1 | Book Stock Details | Total copies of book in library, available copies either as e-Book or hard copy.
5.5.2 | Borrower Details (ADMIN feature) | The search bar shows the details of the specified book stock along with the User ID of the members who have borrowed it,w which can b hard copy or e-Book.
5.5.3 | Borrow feature | This feature enables the user to borrow books.
6 | Member's Profile Page | The profile has all the information of the user | 2021-11-14 | 2021-11-18 | 6 | 3 | 2 | HTML,CSS,Python/JS | Nithish
6.1 | Information | Members information get's updated now and then. The information displayed includes, Contact details.
6.2 | Payment | Payment feature can be accessed from the profile by members. This is used to pay due bills to the librarian. It also displays the list of due and fine payments made by the member.
6.3 | Borrowed Book details | This list shows the list of books the member has borrowed and also mentions its type(hard copy or soft copy) and also shows the issue and due date.
7 | Chat bot | It can be accessed by clicking on the chat icon on the bottom right side. | 2021-11-20 | 2021-11-25 | 6 | 3 |  | Python,AI,ML | Uditi
8 | Admin's profile | Profile can accessed by profile icon on the top right. | 2021-11-25 | 2021-12-02 | 10 | 5 | 1 | HTML,CSS,SQL | Khushi
8.1 | Information | Admins information is automatically updated once the admin creates an account.
8.2 | Payment | All the payments made by the members will be dispalyed to the admin, with all the necessary details.
8.3 | Block Account | The account of any member who haven't returned even after the due for a specified amount time will be disabled until he returns and pays all dues.
8.4 | Member Details | Admin can directly access the member database through this feature.
8.5 | Stock Details | Admin can have accesss to all sections of the book database to review stock.
9 | Payment | Members can use this feature to pay their dues and fine | 2021-12-03 | 2021-12-07 | 7 | 4 | 2,3,6 | HTML,CSS,Python/JS,SQL | Nithish
9.1 | Payments to be made | Displays the list of paymet member has to do
9.2 | Payment gateway | Gateway to make payment to the librarian
9.3 | Authentication & Confirmation | Authenticating the payment and displaying the confirmation message.